## Sheet1
SCRUM PLAN IGVC 2013 CHECKLIST
*Each sprint lasts for 2 weeks unless otherwise stated
[Week 6 of Fall Term]
Sprint 1 | Status | Member Responsible | Client | Problems
Determine if we will stay with current sensors (IMU/ GPS/E-stop/LIDAR,etc.) | OK | Ander & Ruffin | Dr. Mutchler
Choose and place new orders for needed sensors | moved | Ruffin | Dr. Mutchler | Delayed due to budget options
Display RT camera data | OK | Ander | Dr. Mutchler
Display RT LIDAR data | OK | Ander | Chris & Cooper
HUSKY can be remotely controlled (basic operations) | moved | Derek |  | Delayed due to technical problems with ClearPath Robotics
Sprint 2
Display RT IMU data | moved | Ruffin |  | Problems with sensors RS232 communication
Display RT GPS data | OK | Ruffin | Chris & Cooper
E-stop works (wireless and on-board) | moved | Ander |  | Delayed
Choose and place new orders for needed sensors | OK | Ruffin | Dr. Mutchler
HUSKY can be remotely controlled (basic operations) | check? | Derek | any | Needs to check with client
[Start of Winter Term]
Sprint 3
HUSKY can be remotely controlled (advanced speeed operations, e-stop) |  | Derek
Display other sensor RT data |  | Ruffin
Display system telemetry
Record and replay LIDAR and camera data
Record via remote control
Identify the presence of solid objects (not white lines or flags) within 50 ft | OK | Ander | Chris
Identify white lines | OK | Ander | Chris
Move from GPS waypoint to GPS waypoint |  | Ruffin
Capable of sending data in RT back to computer |  | Spencer
Demonstrate code-controlled camera settings (focus, brightness, zoom, etc) | OK | Ander | Chris
Display RT IMU data |  | Ruffin
E-stop works (wireless and on-board) |  | Ander
Sprint 4
Record and replay other sensor data
Distinguish between soldi and dashed lines
Identify the flags
Identify the construction barrels
Identify the trashcans
Indentify the fences
Identify the sawhorses
Identify the cones
Identify anything else
Sprint 5
Avoid obstacles
Plan path for 1 GPS waypoint to another
Travel between solid lines and dashed lines
Display and deal with inconsistent sensor data
Path planning with flag rules
Run the basic course withouth speed considerations
Determine if it is stuck in a corner/gravity well and deal with it
Make new motors turn via software
Get feedback from motors
Sprint 6
Plan path from current position to end position
Rund the basic course at a speed that ensures qualification
Critical error prevention
Run the big course without any speed consideration
Make the new motors turn perfectly under software control
Sprint 7
Integration testing
Integrate with new robot a basic course level
[End of Winter term]
Final Sprint (lasts for the entire Spring term)
Run the big course with an inputted goal speed
Intense system testing
Intense performance testing
Integrate with new robot at an advanced course level